|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **TASK/COMMITTEE** | **WHO IS HANDLING** | **DETAILS** | **DATE COMPLETED** | **BUDGET** |
| **DESIGN** |  |  |  |  |
| Create pocket garden in downtown  | Design Committee & Manager | * Obtain permission to use identified property.
* Acquire garden materials.
* Prepare identified site for plant transfer.
* Obtain volunteers for planting day.
 | * December 2016
 | $2,000 |
| Install new plantings into planter boxes downtown | Design Committee & Manager | * Find sponsors for boxes
* Coordinate planting day with KBB & Master Planters
* Create promotional materials for project~~.~~
 | * Spring Planting May 2016
* Fall Planting

November 2016 | $2500 |
| Sponsor a spring art event | Design Committee Booth Museum Guilds | * Identify event needs
* Purchase infrastructure materials
* Notify artists and obtain entertainment.
 | * May 2016
 | $1,500 |
| Install smoker’s poles around downtown for litter management. | Design Committee | * Take inventory of interested businesses (particularly restaurants)
* Purchase poles.
 | * August 2016
 | $2,300 |
| Research grant sources for implementing design plan, including directional signage. | Manager | * Our Town Grant (NEA)
* GA Humanities
* Million Pollinator Project
 | * Ongoing
 |  |