## Work Plan Overview
Community Work Plan Review Form
2017 Annual Work Plan
Vision Statement |  | Our vision for downtown is a charming and prosperous district that connects our community through the preservation of our history, responding to the present and planning for the future.
Mission Statement |  | The mission of the Downtown Development Authority is to enhance the downtown district by valuing our heritage, combining our creativity and resources to provide a sense of belonging for our citizens and visitors to enjoy our charm and prosperity.
Transformation (implementation) Strategies
Transformation (implementation) Strategy #1:
Arts development
Transformation (implementation) Strategy #2:
Tourism development
Transformation (implementation) Strategy #3:
Top Priorities for Year 2017
Status: |  |  | Goal(priority) #1
Achieved | In Progress | Stalled
In progress/Achieved |  |  | Improve communication with downtown businesses, property owners, and stakeholders.
Goal(priority) #2
Stalled |  |  | Develop greenspace downtown.
Goal(priority) #3
Achieved |  |  | Renew Business Improvement District
Comments on Goal/Priority Status
Improving communication with downtown businesses, property owners, and stakeholders is an ongoing project that has clearly seen gains this year. For 2018 the goal is to quantify what is actually meant by "improve communication" so there are additional actionable efforts for us to work on. Developing more greenspace downtown is on hold until the completion of a sculpture walk, walking tour, and other projects downtown that evovled in 2017. Completing the Business Improvement was a challenge and a significant achievement for the DDA. The renewal will be good until 2022.

## Design
Design Committee
Committee Chair: Lisa Stone
Transformation (implementation) Strategy:
Arts Development
Goal:
Work on completing small projects downtown relative to art and arts development.
Objective
Status | Task | Responsible Party | Cost | Funding Source | Time Line
In progress | Bring rotating Sculpture Walk to downtown | Sculpture Walk Task Force | 5000 | BID Fund | 2018-05-01
Complete | Continue to develop annual Art Market | Art Market Task Force | N/A | Modern Woodmen of America | 2017-05-01
Complete | Improve lighting in parking areas around downtown | DDA Manager & Electric Dept. | N/A | Electric Department | 2017-09-01
Complete | Install additional smoker’s poles around downtown for litter management. | Lillie, Nancy, Sheri | 1200 | BID Fund | 2017-06-01
In progress | Develop new walking tour for downtown. | Lillie, Sheri, Pam, Valerie | 2000 | Keep Bartow Beautiful | 2018-06-01
Partner Involvement
Agency Name |  | Primary Contact |  | Level of Commitment
Keep Bartow Beautiful |  | Sheri Henshaw |  | High
Modern Woodment of America |  | Garth Gherardhini |  | High
Synopsis of Activity:
- Wrote successful grant to GA Council for the Arts to fund Scultpure Walk.
- Wrote successful grant to GA Humanities to fund history walking tour.
- Developed Art Market into larger event and raised $2,500 for DDA from matching funds.
- Worked with Electric Department to install better lights in downtown parking areas.
- Brought new smokers poles to downtown restuarants and establishments to cut down on cigarette litter.

## Organization
Organization Committee
Committee Chair: Maureen Kirkland
Transformation (implementation) Strategy:
Communication
Goal:
Improve communication with downtown businesses and stakeholders.
Objective
Status | Task | Responsible Party | Cost | Funding Source | Time Line
Complete | Revise and update master contacts database | Carol & Cindy | $40/mo. | General Budget | 2017-08-01
Complete | Host Mix and Mingle for downtown businesses | Maureen | 600 | General Budget | 2017-12-01
Ongoing | Identify more partners/sponsors for downtown events. | Maureen, Lillie, Chamber, DDA Board | N/A | N/A | 2018-01-01
Partner Involvement
Agency Name |  | Primary Contact |  | Level of Commitment
Mad Krafter |  | Carol Redman |  | High
Hotel Meeting Match |  | Maureen Kirkland |  | High
Chamber of Commerce |  | Cindy Williams |  | Moderate
Synopsis of Activity:
- Work with DDA staff to identify all businesses, property owners, partners, stakeholders, volunteers, vendors, artists, merchants, performers, et cetera who interact with DDA and provide information to Carol to establish comprehensive database.
- Plan and host mix and mingle for downtown businesses at local resturant.
- Work with Chamber of Commerce to identify new strategy for sponsorship and fundraising including possible leads for funding.

## Promotion
Promotions Committee
Committee Chair: Lara Jeanerret
Transformation (implementation) Strategy:
Arts & Tourism Development
Goal:
To enhance awareness of arts, events, and happenings in downtown Cartersville.
Objective
Status | Task | Responsible Party | Cost | Funding Source | Time Line
Complete | Complete update of See, Shop & Dine Guide | Lara, DDA Staff, DDA Board | 2000 | General Budget | 2017-10-01
Complete | Finalize 2018 event calendar and print rack cards | Maureen, Lara | 200 | General Budget | 2017-10-01
Complete | Print holiday event rack card for all downtown & merchant events | Dan, Lara, Lillie | 200 | General Budget | 2017-10-01
Complete | Establish digital billboard co-op policy | Lillie, Maureen, Promotions Committee | N/A | N/A | 2017-09-01
In progress | Design downtown t-shirt and purchase promotional items | Lara, Jessica | TBD | General Budget | 2018-04-01
Partner Involvement
Agency Name |  | Primary Contact |  | Level of Commitment
It's About Time Boutique |  | Dan Kramer |  | High
Lara J Designs |  | Lara Jeanerret |  | High
Synopsis of Activity:
- Work with board and staff to create and finalize 2018 event cards and 2017 holiday event cards by Bluegrass Festival inOctober.
- Worked with promotions committee to obtain ad space on new digital billboard and then develop policy for cooperative advertising with downtown businesses.
- Working to develop fun and interesting promotional items for DDA.

## Economic Development
Economic Development Committee
Committee Chair: Pam Wilson
Transformation (implementation) Strategy:
Communication
Goal:
Improve communication with downtown businesses and stakeholders.
Objective
Status | Task | Responsible Party | Cost | Funding Source | Time Line
Complete | Renew Business Improvement District | Lillie, DDA Board | N/A | N/A | 2017-05-01
In progress | Improve website content | Lillie, Lara, DDA Staff | N/A | N/A | 2018-03-01
In progress | Work with developers to bring housing development to downtown | Lillie & outside partners | N/A | N/A | 2019-01-01
Partner Involvement
Agency Name |  | Primary Contact |  | Level of Commitment
Lara J Designs |  | Lara Jeanerret |  | High
Synopsis of Activity:
- Successfully renewed Business Improvement District with 57% majority vote.
- Working to improve website content and make more accessible to average user with changes to calendar, ability to list events, real estate listings, etc.
- Working to bring housing development project downtown.